## Slide 1: Point Hudson Breakwater Improvement Project
Port Commission Meeting
June 2020

## Slide 2: Introduction
Background
Breakwaters
Port Townsend
Point Hudson
SOUTH JETTY
NORTH JETTY

## Slide 3: Introduction
The breakwaters were constructed in 1934 by the military.
  Major rehabilitation was performed in 1969, with additional retrofit of the breakwater ends performed in 1996.
Site Overview
Shoal
Shoal
Narrow Entrance
Typ. Vessel Approach
Sediment Drift
Marina Basin
Beach Erosion
Waves from ESE
Waves from S
1934 Original Construction
1969 Rehabilitation
1996 Partial Rehabilitation

## Slide 4: Introduction
Timber piles, walers, cable tiebacks, and armor rock are at or beyond useful life. Stability of the overall structural system is compromised.
  The most advanced structural deterioration was observed at the end of the south breakwater.
  Voids in the riprap reduce the system’s wave protection capability.
Existing Condition
Pile Deterioration
Stone Deterioration
Structure Failure
Cable Deterioration
Waler Deterioration

## Slide 5: A Challenging Marine Environment
  A 2018 storm damaged the breakwaters, breaking pile tops, severing cable ties and further eroding the armor rock core.
  Constructing the Replacement Breakwater is the first step in building resilience for Point Hudson’s future.
A December 2018 storm sweeps over the jetties and into the Point Hudson Marina.
Photo taken by Ron Moller

## Slide 6: Design Objectives
The guiding objectives are to provide a breakwater rehabilitation/replacement design that:
  Provides wave protection for the Point Hudson Marina for a minimum design life of 30 years.
  Responds to community concerns to maintain the aesthetic of the existing breakwater.
  Can be permitted, constructed and maintained.
Overview

## Slide 7: Design Objectives
  Engineering. Protect existing marina and Port operations for 30 years from wind and vessel waves and sea level rise.
  Aesthetics. Similar in appearance to existing breakwater (rocks and piles) using environmentally acceptable materials.
  Environmental Considerations. Remove creosote, reduce breakwater footprint, and protect existing eelgrass outside of marina.
  Constructability. Minimize risks from potential cost overruns, delays, errors, and obstacles during construction.
  Cost. Efficient design that minimizes maintenance costs.
Replacement breakwater height must include sea level rise resistance
Environmental Considerations: Remove rock and debris within 10 ft of the base
Environmental Considerations: Reduce Footprint

## Slide 8: Alt. Evaluation: Encapsulation vs. Replacement
~2.5’
~10’
Existing structure remains except for a few select creosote timber piles removed for permitting.
Piles driven in a batter outside of existing structure, expand footprint by 2.5 ft each side with mesh lagging.
Reduces demo costs but increases offsite mitigation costs.
Existing structure is completely removed including piles and rock.
Piles driven batter with new rock installed between the rows of piling.
Seeks to be self mitigating because of the reduction in footprint and creosote removal.

## Slide 9: Breakwater Design
After review of the different alternatives, stakeholders selected replacement as their preferred alternative with some additional input.
In addition to selecting replacement as the preferred design, the stakeholders presented the following suggestions and guidance:
Stakeholder Input
Category | Input
Pile | Piles should be closely spaced, similar to the existing Piles should be uncoated steel pipe piles with sacrificial corrosion thickness, no composite piles Piles should be battered to match existing aesthetics Piles should be supported with tie rod cross-ties and potential walers
Breakwater Core | Large high quality riprap (granite) No mesh for rock containment
Walkway | Design and system should allow for installation of walkway on top of the south breakwater End of walkway waterside should incorporate a wider turnaround and look out area
Permitting | North and south breakwaters should be designed and permitted together

## Slide 10: Selected Breakwater Design - Replacement
Selected Cross-Section and Elevation
Tiebacks & Walers on Top of Piles
New Battered, Uncoated Steel Pipe Pile
Section A - A
A
New Walkway
New Battered, Uncoated Steel Pipe Piles
A
New 8’ Wide Walkway
New Large Armor Stone
Elevation View
Piles spaced 3 ft- on center, TBD in final design

## Slide 11: Environmental Goals and Benefits
1934 Original Construction
1969 Rehabilitation
ENVIRONMENTAL PERMIT GOALS:
1. AVOID RE-INITIATING CONSULTATION WITH NMFS
2. DESIGN A SELF-MITIGATING STRUCTURE
ENVIRONMENTAL BENEFITS:
1. CREOSOTE REMOVAL 827 piles (~ 250 tons) + walers
2. SMALLER FOOTPRINT (~12 %)
3. ROCK AND DEBRIS REMOVAL within 10 ft of jetties

## Slide 12: Project Schedule
Scenario 1 – Best Case (Goal)
Construction Completion Spring of 2022

## Slide 13: Other Potential Permitting Scenarios/Schedules
 | Scenario 1 (Best Case) | Scenario 2 | Scenario 3
Description | Existing permit is modified for current design | Existing permit is modified but NMFS is re-engaged | Modification is rejected and a new permit application is required.
Permitting Length | 6 months | 12 months | 18 + months
Permit Submittal | July 2020 | July 2020 | July 2020
Permit Received | Jan 2021 | July 2021 (+6 months) | Jan 2022 (+12 months)
Bid Advertisement | Spring 2021 | Spring 2021 | Spring 2022 (+12 months)
Construction Start | Fall 2021 | Fall 2021 | Fall 2022 (+1 year)
Construction End* | Spring/Fall 2022 | Spring/Fall 2022 | Spring/Fall 2023 (+1 year)
*Would seek to replace breakwater in one construction season however, depending on fish work window requirements, replacement may need to occur over two in water work windows.

## Slide 14: Summary
  Replacement Alternative
  Breakwater replacement alternative similar in style as existing breakwater with modern materials and walkway on south breakwater.
  Permitting
  Permitting will include replacement of both breakwaters.
  Final Design
  Final design will be for replacement of both breakwaters.
  Project Bidding for Construction
  Bid Documents developed for replacement of south breakwater first.
  Schedule
  Earliest completion of the south breakwater replacement is spring or fall of 2022.

## Slide 15: Project Costs
  Total Project Costs (South and North)
  Construction Cost - $12.5 Million (2020 dollars)
  Engineering, Permitting, Bid Docs - $394,000
  Construction Administration (South) - $250,000
  Construction Administration (North) - $250,000
  Grand Total = $13.39 Million (2020 dollars)
  Total Project Costs (South Replacement Only)
  Construction Cost - $7 Million (2020 dollars)
  Engineering, Permitting, Bid Docs - $373,000
  Construction Administration (South) - $250,000
  Grand Total = $7.62 Million (2020 dollars)
  Variables
  Costs assume two separate construction seasons which is most likely scenario due to funding and potential fish window restrictions
  Permitting from scratch (Scenario 3) would increase permitting costs
  Costs include the new walkway on the south breakwater
  Does not include cost inflation
  Cost does not include offsite mitigation costs that could be required (0%-5% of project costs)
  Cost does not include potential repairs needed to the existing breakwaters while waiting for replacement

## Slide 16: Next Steps
  Submit Permits
  Complete Final Design

## Slide 17
Questions?