## Slide 1: Port of Port Townsend
Boatyard General Permit
Stormwater System

## Slide 2: Permit Authority
Boatyard General Permit issued
BGP reissued in 1997
BGP reissued again in 2005
2005 BFP was appealed
  a court settlement included “pilot” testing of treatment technologies in 2007-8
  An Economic Analysis – AKART (All Known Available and Reasonable Treatment) Study was initiated as part of this adoption, and completed in 2010
The permit has been subsequently reissued in 2011 and in 2016
Clean Water Act
  National Pollutions Discharge Elimination System
  Title 33 USC § 1251 et seq.
WA Water Pollution Control Act
  RCW 90.48
  Boatyard General Permit
  Industrial Stormwater General Permit
    WPPA Washington State Marine Terminal AKART and ISGP Corrective Action Guidance Manual

## Slide 3: Chronology
1996 stormwater installed
  Designed by Reid Middleton
  Conveyance
  Sand Filters – perimeter & in-traffic
2010 system upgrade
  Stormwater Rx units (2 of 4 main sub-basins)
  Ecology funded $332k of $495k
2013 Notice of Intent
  Waste Action Project

## Slide 4: Chronology - continued
Settlement with WAP
2014 Level Three (3) response action
  six (6) benchmark exceedances of zinc during the second quarter 2013
  six (6) exceedances of copper in late 2013
  August 2014 - Port had installed and implemented (Landau)
    Escalating Level One (1) Source/Operational Controls
    Level Three (3) Treatment Systems
      Improvements to perimeter sand filters
        Failed installation discovered
      Reconfigure vaults & add oyster shells (biochar substituted)
      Bench testing & pilot of biochar – downspout tote
      Biochar coffyns installed

## Slide 5: Chronology – continued
PPTBH continued to exceed the benchmarks for zinc and copper
Sampling point changed from Outfall A to 4 catch basins in 2016
Port & Ecology meeting in spring 2016
Administrative Order – issued June 17, 2016
  Revised Engineering Report
  The advanced treatment BMP shall be installed and implemented on or before September 30, 2017.

## Slide 6: Engineering Report
Parametrix selected
  Recommended Alternative
    Bio-infiltration
    Cost - $1.2 to $1.8 million
    Area ~20,000 sq ft
  Phased implementation
  Segregated Basins

## Slide 7: Phased implementation
2017 Construct Phase 1 Infiltration Basin
  Connect Vault 1 Lift Station to Phase 1 Infiltration Basin
  Relocate Boatyard Aquip Unit to Vault 2 and Replace Media with Biochar
  Estimated Cost $400,000 ( Grant $200,000 – Port $200,000)
2018 Construct Return Flow Lift Station at Outfall A
  Install Tide-Flex Valve on Outfall A
  Run Force Main from Lift Station to Phase 1 Infiltration Basin
  Estimated Cost $500,000 ( Grant $250,000 - Port $250,000)
2019 Construct Phase 2 Infiltration Basin (doubles capacity of Phase 1 infiltration)
  Estimated Cost $400,000 (Grant $200,000 – Port $200,00)

## Slide 8: Segregated Basins
Technical Memo (January 25, 2017)
  Source BMPs
    Removal of contaminated soils
    Jetting of conveyance pipes
    Cover of work areas
  Conclusions
    Reduce infiltration area by 20%
    Twenty year life cycle costs

## Slide 10: Modifications to Existing System

## Slide 12: Infiltration vs System Modification
Meets AKART adaptive management
Order of magnitude lower initial cost
Little if any impact to operational land area
Can be paired with long term facility planning
Potentially can be paired with Integrated Planning Grant
System Modification
May meet Ecology’s “Advance Treatment BMP” requirement
Order of magnitude higher initial cost
Significant impact to operational land area
Need to settle issue of treatment quantity
Infiltration

## Slide 13: Crossover from Industrial Stormwater General Permit
Permittees must fully implement the stormwater treatment approach included in their Ecology-approved Engineering Report as soon as possible, but not later than September 30th of the year following year following the calendar year during which the Level 3 Corrective Actions were triggered, unless an alternate date is specified in an order.
Permittees may engage Ecology to determine whether the treatment facility installed under the previous Level 3 can be upgraded to more effectively treat stormwater. Stormwater treatment system upgrades are anticipated to include modification of the existing treatment system, including additional upgrades and/or potential structural additions. In some cases, the existing treatment system may be augmented by a pretreatment or polishing step (i.e., expanded treatment train). The Permittee’s plans for treatment system upgrades must to be submitted to Ecology for review and approval in an engineering report.

## Slide 15: 2016 Boatyard General Permit
Requirements for Level 3 Response
  Engineering report within 60 days of 6th exceedance
  Implementation within 12 months of Ecology’s acceptance of Engineering report
Ecology recognizes that the BGP is silent on requirements for when a Level 3 response does not meet benchmarks

## Slide 16: Recommendation
Request modification to Administrative Order
  Timeline to submit a revised engineering report
  Timeline for 12 months to install approved engineering report
Approve staff to seek a proviso for an Integrated Planning Grant